Costing Prototype

**Date:** Friday, September 30th, 2016.

**Prepared by:** Ing. Liseth Patricia Jiménez Torres.

|  |  |
| --- | --- |
| Summary of this week | |
| Current Sprint | Sprint 10 |
| Duration of Sprint | September 27 – October 4 de 2016 |
| Scope of the Sprint | Warehouse, Minor Changes. |
| Progress of the Sprint | 56% (121.5 hours of 214 hours planned) |
| Team for this week | Steven Boada: 47  Andrés Gómez: 47  Claudia Rey: 38  Luna Granados: 42.5  Liseth Jiménez: 23 |

Activities Carried Out:

This week, the following activities were carried out:

1. Revision of the developed interfaces and bettered the presentation according to the standards of the international office.
2. Adjustments were made to the code settings in order to comply with the standards at the international office.
3. Started the implementation of the tasks about: **Withdrawals, Returns and Expiration of materials**
4. Analysis of report about **Control meals**.
5. Attending Functional Meetings.
6. Meetings with Yulia for analyze next requirements.

Activities planned for next week

1. Adjust the settings of any abnormal behavior needing correction reported by Yulia during the review of the last uploaded version of the system draft.
2. Perform quality code settings to meet the development standards of the iOffice.
3. Continue analyzing of UI about **Control meals.**
4. Continue the implementation of the tasks about: **Withdrawals, Returns and Expiration of materials**
5. Deploy in QA a new version of the project with adjustment.
6. Meetings with Yulia for analyze next requirements.