**Prototype costs**

**Date:**Friday, March 4, 2016.

**By:**Ing. Liseth Patricia Jimenez Torres

|  |  |
| --- | --- |
| **Summary of this week** | |
| **Current Sprint** | Sprint 6 |
| **Duration of the Sprint** | 29 January - 18 March 2016 |
| **Scope of the Sprint** | Lines, Deposits, Transactions, Transaction Types, Activities And Materials, Bean Index Report By Section. |
| **% Progress of the Sprint** | 69% (178 hours of 257 planned hours) |
| **Team work this week** | Marisol Calderón: 12 hours  Steven Boada: 25 hours  Gerardo Herrera: 22 hours  Andrés Gómez: 24 hours  Liseth Jiménez: 23 hours |

**Activities carried out**

The following activities were carried out in this week:

1. Review of the interfaces developed so far and improve the presentation according to the standards of the ioffice. These cosmetic changes will be included in the next version of the project.

2. Review of the documents sent by Yulia (**Cycles, Warehouse**).

3. Continued the implementation of the functionality of the modules: **Cycles and Deposits**.

4. Continued the implementation of the report **Bean Index--By Sections.**

5. Daily meetings with Yulia were made to let her know the progress of the sprint.

6. Continued documentation and contextualization of the requirements of sprint 6.

7. The creation of the entity model continued relationship tool Enterprise Architect.

**Bug reported**

The following bugs were generated during this week:

|  |  |  |
| --- | --- | --- |
| **Bug No.** | **Description** | **State** |
| 9941 | Activities can be added to crops newly registered in the database. | New |

**Activities planned for next week**

1. Continue the implementation of the module **Cycles**.

2. Continue the implementation of the module **Deposits**.

3. Continue the implementation of the report **Bean Index--By Sections.**

4. Review of the documentation for the sprint 6.

5. Review of the tasks implemented by the Working Group for sprint 6.

6. Daily meetings with Yulia for project monitoring.

7. Adjustments of any corrections or abnormal system behavior reported by Yulia during the review of the latest project upload.

8. Quality code adjustments to meet the standards of development of the IOffice.