Costing Prototype

**Date:** Friday, April 22nd, 2016.

**Submitted by:** Eng. Liseth Patricia Jiménez Torres.

|  |  |
| --- | --- |
| Weekly Summary | |
| Curent Sprint | Sprint 7 |
| Duration of the Sprint | March 29 – Aprill 26, 2016 |
| Scope of Sprint | Withdrawals, Deposits, Transactions, Purchase Invoices, User Interface Changes. |
| % of Sprint Advance | 100% |
| Team work this week | Marisol Calderón: 2 hours  Steven Boada: 46.5 hours  Gerardo Herrera: 14.7 hours  Andrés Gómez: 18 hours  Liseth Jiménez: 23.5 hours |

Activities Performed

In this week the following activities were carried out:

1. Review of the interfaces developed to date and improve their presentation according to standards of the iOffice. These cosmetic changes will be included in the next version of the project.
2. The analysis of the documentation requirements for Sprint 7 was finished.
3. Implementation of the **Purchase Invoices**, **Transaction Adjustment**, and **User Interface Changes Deposits** modules was completed.
4. We continued to create the entity relationship model in the Enterprise Architect tool.
5. Code quality adjustments were made to meet the development standards of the iOffice.
6. We worked on solving the bugs Yulia reported.
7. A new version of the project was deployed in QA.

Bugs Reported

During this week we worked on the following bugs.

|  |  |  |  |
| --- | --- | --- | --- |
| **Bug #** | **Description** | **State** | **Reported Date** |
| 9958 | Activity with today's date can be created under Crop that has initial and final dates outside of the range. | Assigned | April 8, 2016 |
| 9961 | Duration should be auto-populated based on the activity length. | Resolved | April 13, 2016 |
| 9964 | Labels in Deposit Form don't match data. | Resolved | April 19, 2016 |

Activities planned for next week

1. Continue resolving the outstanding bugs.
2. Perform reviews and tests of the tasks implemented by the working group for the Sprint in July.
3. Daily meetings with Yulia for project monitoring.
4. Adjust the settings of any abnormal behavior needing correction reported by Yulia during the review of the last uploaded version of the system draft.
5. Perform quality code settings to meet the development standards of the iOffice.