**Prototype costs**

**Date:**Friday, February 19th, 2016.

**By:**Ing. Liseth Patricia Jimenez Torres

|  |  |
| --- | --- |
|  | **Summary for this week** |
| **Current Sprint** | Sprint 6 |
| **Duration of the Sprint** | 27 January - 29 February 2016 |
| **Scope of the Sprint** | Lines, Deposits, Transactions, Transaction Types, Activities And Materials, Bean Index Report By Section. |
| **% Progress of the Sprint** | 69% (99.5 hours of 144 hours planned) |
| **Team work this week** | Marisol Calderón: 10 hours  Gabriel Moreno: 11 hours  Steven Boada: 22.5 hours  Sergio Ortiz: 22.5 hours  Liseth Jiménez: 15 hours |

**Activities carried out**

The following activities were carried out in this week:

1. Review of the interfaces developed so far and improvements in its presentation according to the standards of the ioffice. These cosmetic changes will be included in the next version of the project.

2. Review of the documents sent by Yulia (KPI Analysis MR-V2, Warehouse).

3. Continued the implementation of the functionality of the **Cycles**.

4. Continued the implementation of the **Bean Index--By Sections** report.

5. Daily meetings with Yulia were made to let her know the progress of the sprint.

6. Started documentation, joint and contextualization of the requirements of the system.

7. Began the creation of the entity model relationship tool Enterprise Architect.

8.  Reorganized the tasks in Xplanner.

9. With Yulia and the Working Group, we established a new process for the implementation of the project for each sprint, based on the Scrum methodology.

**Activities planned for the next week**

1. Review of the documentation for Sprint 6.

2. Review of the tasks implemented by the Working Group for Sprint 6.

3. Daily meetings with Paul and Yulia for project monitoring.

4. Adjustments of any corrections or abnormal system behavior reported by Yulia during the review of the latest updated version of the project.