**Prototype costs**

**Date:**Friday, April 1st, 2016.

**By:**Eng. Liseth Patricia Jimenez Torres.

|  |  |
| --- | --- |
| **Summary of this week** | |
| **Current Sprint** | Sprint 7 |
| **Duration of the Sprint** | March 29 - April 26, 2016 |
| **Scope of the Sprint** | Lines, Purchase Invoices, Deposits, Transactions, User Interface Changes. |
| **% Progress of the Sprint** | 27.5% (79.5 hours of 289 planned hours) |
| **Team work this week** | Marisol Calderón: 6.5 hours  Steven Boada: 47.5 hours  Gerardo Herrera: 21.5 hours  Andrés Gómez: 30 hours  Liseth Jiménez: 25 hours |

**Activities carried out**

The following activities were carried out in this week:

1. Review of the interfaces developed so far and improve the presentation according to the standards of the ioffice. These cosmetic changes will be included in the next version of the project.

2. Began analysis of the documentation requirements for Sprint 7.

3. Started the implementation of the modules **User Interface Changes and Purchase Invoices, Adjustment Transaction.**

4. We continued the development of the entity model relationship in the Enterprise Architect tool.

5. Were carried out quality code settings to meet the development standards of the IOffice.

**Activities planned for the next week**

1. Continue the analysis of the documentation for Sprint 7.

2. Continue the implementation of the requirements of Sprint 7.

3. Daily meetings with Yulia for project monitoring.

4. Adjustments to any corrections or abnormal system behaviors reported by Yulia during the review of the latest project upload.

5. Quality code adjustments to meet the development standards of the IOffice.